## Sheet1
SL No. | FR | Feedback After UAT | Status | Feedback After Fixation | Priority | FR No | Status For Business UAT | UAT Conducting Date | Final Status
1 | FR 1 | 1. The following heading should Rename in both Cluster Market Add/Edit. *. Name = Cluster Name *. Value From = Market Val. From 2. Issue: data did not show in the list after click on save button. | Completed |  | P1 | FR 1 | Completed | 2022-06-01 | PASSED
2 | FR 2 | 1. "Morning Table View" and "D-1 data" pages Excel will get downloaded by clicking on item. 2. In Retailer Pending Verification "LoginName to Change By" in Excel. 3. Provide sample data. | Completed | 1. Need to provide Sample data in every Export Excel. | P2 | FR 2 | Completed
3 | FR 3 | 1.Retailer ID must be Added in “SMART SEARCH” 2. “Category” (label) should be renamed. (Which category? Need to write name after category to understand. | Completed |  | P1 | FR 3 | Completed | 2022-06-01 | PASSED
4 | FR 4 |  | Canceled |  | P1 | FR 4 | Canceled
5 | FR 5 | 1. "Date Retailer App Login" must be changed to "Date Wise Retailer Ap Login". | Completed |  | P2 | FR 5 | Completed
6 | FR 6 |  | Ready For Technical UAT |  | P2 | FR 6 | Pending
7 | FR 7 | 1. In "SC Range" all data must show in the list. 2. In Marchendiser Contact No. Search (with or without "0") should work or not. (Decession pending from Babu vai) 3. In "SC Range", "Merchandiser Contact No.", "TMO Contact NO." table data front must be as same as DMS Live Developrd front. | Completed |  | P2 | FR 7 | Completed | 2022-06-06
8 | FR 8 |  | Completed |  | P1 | FR 8 | Completed | 2022-06-01 | PASSED
9 | FR 9 |  | Not Completed |  | P2 | FR 9
10 | FR 10 | 1. For Business UAT test data/sample data must be provided to business. 2. In Issue To Retailer "Status" must renamed to "Inventory Owner" Status. 3. In "Audit Report Product Wise" "Device Name" must be changed to "Product Name" as dropdown menu and multiple selactable checkboxes system. 4. In "Audit Report Summary" data list view "Return-issue to retailer count" must be renamed as "Return-reissue to retailer count". Add Count in "Return_To_WH_Intact", "Return_To_WH_faulty", "MigratedOtherDD" 5. In "Device Overview Report" the column "Return_To_WH_faulty" must be renamed and worked as "Return_To_WH_faulty_Count" | Completed |  | P2 | FR 10 | Completed | 2022-06-06
11 | FR 11 |  | Not Completed |  | P2 | FR 11 | Completed
12 | FR 12 | 1. Order By (descending) LIFO the newly saved User Feedback Response. 2. “Page Link” Font hight should be as like “Page URL” 3. In Category: Value (User friendly, Interactive etc.) Should be in same line with comma separated. 4. The Feedback pop-up window view issue after submitting with any non-valid information. | Completed/RTUAT |  | P2 | FR 12 | Completed
13 | FR 13 | Technical UAT done by Awlad and Minhaz vai but the FR are not competely functional | Not Completed |  | P1 | FR 13 | Completed
14 | FR 14 |  | Completed |  | P2 | FR 14 | Completed
15 | FR 15 |  | Partially Completed | Need confirmation from Minhaz vaai. | P1 | FR 15 | Completed
16 | FR 16 |  | Ready For Technical UAT |  | P1 | FR 16 | Completed
17 | FR 17 |  | Completed |  | P2 | FR 17 | Completed
18 | FR 18 | 1. In "ID Type *", after selecting "NID" the * "Identification No." must be change to "ID No". 2. //If Possible, "Scrolling" option and "Select All" check box must be added for Selecting "Route" in Define Merchandiser page.// 3. In "Merchandiser List" Add New operation after adding new Merchandiser the newly saved data must be Order By (descending) LIFO in Merchanidiser List view. | Completed/RTUAT |  | P2 | FR 18 | Completed
19 | FR 19 |  | Completed |  | P1 | FR 19
20 | FR 20 |  | Canceled |  | P2 | FR 20 | Canceled
21 | FR 21 | 1. Only Count should be shown against of each user type for every specific week. 2. Need 2/3- different weeks data for testing purpose. | Completed |  | P2 | FR 21 | Completed | 2022-06-06
22 | FR 22 | 1. In MERCHANDISER ATTENDANCE REPORT, in "Attendance Details" downloaded excel file "Merchandiser Code" data need to check as per business logic. (Existing data are RSO Code) 2. "Merchandiser Attendance Summary" need to check with business logic. | Not Completed |  | P1 | FR 22 | Completed
23 | FR 23 | 1. Need to check EV Balance Return Request from "Retailer App" and "DMS" at the same time. 2. Need to check EV Balance Return Request from "DMS". 3. Need to check EV Balance Return Request from "Retailer App". | Completed |  | P2 | FR 23 | Completed
24 | FR 24 | 1. "DISTRIBUTOR STOCK FLOOR REPORT" must be changed to "DISTRIBUTOR SC STOCK FLOOR REPORT" or "DISTRIBUTOR STOCK FLOOR REPORT (SC)" | Completed |  | P2 | FR 24 | Completed