## DMS_2022
DMS - NEW CR 2022- Development Execution Plan
[6 empty] | Dev End |  | QA End
SN | FR from BRS | Task | Task Details | Priority | Developer | Dev End date | Dev Note | Testing Date | Test Note
1 | FR 1 (DMS) | Cluster Market Concept: Cluster Market will not impact the existing Hierarchy concept of DMS. It will be additional mapping for distributor which will be used for reporting and more granular monitoring purpose | 1. UI to create and EDIT cluster names; ID, CM Name, Description, Market value range (business value in money from amount to amount range), remarks; Current CM list generate. 2. Download format and UI to upload distributors vs CM name (Distributor Code, CM Name) 3. Include CM in reports (RDB, itopup (lifting, balance, sale), SIM lifting, SIM Issue, SIM channelfill, SC Channel fill reports.) 4. Current CM – Distributor tagging generate (CM, Distributor code, Name, Region, Cluster region, territory code, Master SIM) | P1
2 | FR 2 (RSO, DMS) | Automated triggers In Notification section (if required Notification section revamp) | 1. Morning (Opening) Table view a. Zero Stock retailer count (count, pressing on count will generate details (Retailer code, itopup number, rso code, product code, stock count) in excel) (as per DMS/MDMS existing logic) b. Low balance retailer count (count, pressing on count will generate details in excel (Retailer code, itopup number, rso code, product code, stock count) (as per DMS/MDMS existing logic) c. MTD Target Achievement with required rate (count, pressing on count will generate details in excel (KPI Target, KPI Achievement, KPI run rate, KPI required rate)) (as per MDMS) d. SAF rejection count (count, pressing on count will generate details in excel) : (Retailer code, MSISDN, rejected reason, activation date) 2. System updates from D-1 data a. Retailer with No route count (count, pressing on count will generate details in excel) (Retailer code, itopup number) b. Retailer with no RSO (count, pressing on count will generate details in excel) (RSO Code, SR Number) c. Retailer with no BTS (count, pressing on count will generate details in excel) Retailer Code, Thana d. Device with no retailer (count, pressing on count will generate details in excel) SL/IMEI, Product Name e. Retailer verification pending (count, pressing on count will generate details in excel) (Retailer code, itopup number, change date, changed by) f. RSO Verification pending (count, pressing on count will generate details in excel) (RSO code, SR itopup number, change date, changed by) | P2
3 | FR 3 (DMS) | Addition in existing: | Bulk upload process of retailer NID a. A new upload module b. Retailer code, NID fields will be uploaded c. Validation Retailer code exists in DMS, NID (10/13/17 digits and number only) d. On the verification page, retailer code, old NID, New NID will appear, ZM will review and verify at one go. Excel export of verification pending. a. Pending Receive SIM from retailers b. Pending retailer verifications c. Pending RSO verifications d. Pending Supervisor changes e. Pending Merchandiser Changes a migrated retailer having Old DD RSO codes in the retailer list and should be removed while transferring from old to new DD | P1
4 | FR 4 (Retailer app/DWH) | Multiple device login vetted by ZBM role and visibility on multiple device of retailers, retailer app Integration (INT) | 1) Multiple device login option will be approved by ZM (if more than 2/3 configurable), with multiple device allowed count. a. For registration of 3rd / 4th device an approval will appear in transaction > verification > Device registration approval page. b. Retailer code, itopup number, SR number, device registered count, new device id, Handset model, request date; fields will appear. c. ZM will approve or reject. d. The request will be sent to retailer app database, API integration with retailer app. e. List of pending approval with same fields can be exported in excel. 2) On device registration, list will appear in report format. Registered devices: retailer code, Device IMEI, Handset Model, Name, Unique Device ID, registration Date, modified date; filter: snap date, retailer code, distributor code 3) Device wise contribution: Retailer code, itopup, Distributor code, Region, Device IMEI, Handset Model, Name, Unique Device ID, date, deno amount, ev amount, IRIS amount. Filter: date, retailer, itopup. (Source DWH/Retailer App) | P1
5 | FR 5 (Retailer app / DWH) | Report data from retailer app / DWH : (int+ext) | 1) Device IMEI, Handset Model, Name, Unique Device ID, Login, Date; filter cluster, region, date 2) Device IMEI, Handset Model, Name, Unique Device ID, Login, Date/time; filter retailer code, date 3) Retailer Code, Device IMEI, Handset Model, Name, Date, time, c2s amount, mode (regular / iris/ deno) customer MSISDN; filter startdate, enddate, Region, Distributor, retailer, customer msisdn (input) 4) Retailer code, Distributor code, region, App Login 1st date, App, App hit count, SIM hit count, deno count, deno amount, EV count, ev amount, IRIS count, IRIS amount. 5) Retailer Code, itopup number, Device IMEI, Handset Model, Name, Date, time, Action: EV PIN reset; Filter retailer code, ev number, date 6) EV PIN Reset Log: Cluster, Region, Distributor, Retailer code, itopup number, request date/time, reset by, temp PIN date time, reset datetime ; Filter date, region, retailer (input), itopup (input) 7) EV PIN Unbar Log: Cluster, Region, Distributor, Retailer code, itopup number, request date/time, unbar by, unbar datetime, Filter date, region, retailer (input), itopup (input) | P2
6 | FR 6 (DMS) | Issued device should be migrated to new DD when retailer migration to another like SIM/SC migration | Issued device should be migrated to new DD when retailer migration to another like SIM/SC migration | P2
7 | FR 7 (DMS) | Smart Search | • By merchandiser contact number option • By TMO Contact • Biometric device… check DMS 1st • In search result by retailer code or itopup or contact number service details like SSO, itopup, SC, type, service point required. It means adding few more flagging in retailer search result. • SC range (start SC serial, end SC serial), search output same as current SC search output | P2
8 | FR 8 (DMS) | In Add/Edit Retailer Type, | o introduce ZONECODE flagging. o All available zone (  ALTBAN  BLKBLK  KHLBAR  COMSOU  CHINOR  CHISOU  CTGMET  COMNOR  D2DDWT  DEVNAT  DHKEAS  DHKSOU  DHKWES  DHKNAR  DHKTAN  DHKOUT  DHAGAZ  MYMMYM  EBEEBE  KHLKHL  KHLKUS  KHUJES  SYLSYL  RAJBOG  BOGBOG  RAJRAJ) will load for each retailer type, o User will assign zone-codes for each type o In retailer type of retailer page, retailer types will be available in dropdown list as per configuration above. | P1
9 | FR 9 (DMS) | POSM Product | POSM Product Return with approval o User returns products from retailer to DD o User choses product and enter count, system validates floor count vs return count, submit return products from DD floor to WH ; for success will be available in pending list for approval, for failure error message with actual reason. o User approves return to WH o Product is deducted from DD Floor o A return report will be found. Distributor, product, count, return verified date. POSM Product Write-off with approval o Write-off from retailer  User choses product and enter count, system validates floor count vs request count, submit writeoff products; for success will be available in pending list for approval, for failure error message with actual reason.  User approves  Product is written – off o Write-off from distributor  User choses product and enter count, system validates DD floor count vs request count, submit write-off products; for success will be available in pending list for approval, for failure error message with actual reason.  User approves  Product is written – off | P2
10 | FR 10 (DMS) | Change in ISSUE TO RETAILER, RECEIVE DEVICE FROM RETAILER: include Retailer search | Change in ISSUE TO RETAILER, RECEIVE DEVICE FROM RETAILER: include Retailer search Include details in DEVICE STOLEN INFO page Audit Report : Assigned to Distributor, Device Name, Device Code, Lifting Date, Distributor Floor count, issue to Retailer count, retailer faulty, Stolen, Returned to WH (intact), return-reissue to retailer count, return to WH (faulty). (Internal as per role) Status wise report | P2
11 | FR 11 (DMS) | Mark retailer’s device as faulty / damaged (Same Process of marking sim as faulty.) | Faulty / damaged device return to WH  Go to Device return to WH  All faulty marked devices will be available for return  Select return to WH  The request will be pending for ZM approval  On ZM approval the devices will be marked as returned to WH  A returned to WH Device list (excel export) will be generated, without any filter. Format: Distributor, Serial, product code, Issue date, Return date. | P2
12 | FR 12 (DMS) | User Response and Feedback capturing : |  User will able to visit a page to log feedback  Rating will be introduced during feedback (1-10)  5 categories will be rated (User friendly, Smooth Operations, faster response, useful content, interactive)  User will enter feedback in Bangla and English (Date automatically captured, user (captured), Subject, details) In Admin Section | P2
13 | FR 13 (DWH+DMS) | Site wise KPI report in DMS (l KPI by admin user) | Existing logic, in external KPI will be lesser, in internal full view. Filter Date, Thana. | P1
14 | FR 14 (DMS) | Deno Checking daily User count (9133) | Deno Checking daily User count (9133) MSISDN, Date, Deno, Count of request Filter: from_date,to to_Date, Deno Admin module, Internal and only exposed to Admin. | P2
15 | FR 15 (DWH+DMS) | Site wise report revamp (both mail communication and DMS new report FR#13) | Include 4G data and information Include Site information Include new KPI Tracking on report read Source DWH & DMS | P1
16 | FR 16 (DMS) | SRAN Site Tagging option in BTS site list of DMS | SRAN Site Tagging option in BTS site list of DMS Include SRAN Flag in Site wise reports FR 13 and FR 15. | P1
17 | FR 17 (DMS) | Retailer Database (Internal, External and Dump) revamp. |  Include fields (retailer TIN, Disable / terminated Date, Terminated (Y/N).  DUMP issue resolve o Heads are broken to next line : RSO_CODEBTS_CODE route1 route2 route3 route4 route5 route6 route7 route8 o Address spaces impacted next record, handle in exports. o Blanks in record | P2
18 | FR 18 (DMS+RSO) | TMO option eliminate and redesign Merchandiser structure. | Keep RSO app team aligned so that the changes not impact Merchandiser App Include TMO new features | P2
19 | FR 19 (DMS) | DMS Dashboard Revamp | DMS Dashboard Revamp | P1
20 | FR 20 (DMS) | In BTS Information, inclusion of Bangla Fields | Address, Thana, District, Division Include missing 4,5 fields | P2
21 | FR 21 (DMS+DWH) | Weekly Update (Generate Report) | a. KPI (Retailer, RSO, BTS, DD, Supervisor, Merchandiser) b. Select Week (last 4 weeks) W1 (Jan1 – Jan7)-W52 (dec25-dec31) c. Press generate d. Format: Type, New count, Edit Count | P2
22 | FR 22 (DMS +RSO) | In merchandiser New/edit page include Designation column. | In merchandiser New/edit page include Designation column.  Merchandiser Attendance details report from MDMS. Merchandiser Code, Contact number, retailer code, product code, Qty, date, Check-in time, Checkout time, time spent. Filter date.  Merchandiser Attendance Summary report : Merchandiser Code, Contact number, retailer count, Qty, date, total time spent.: filter date | P1
23 | FR 23 (DMS) | EV balance return option in DMS | EV balance return option in DMS | P2
24 | FR 24 | Distributor Stock Floor Report (SC) | Distributor Stock Floor Report (SC) | P2